## Social Media Plan Template
Event Planning Template
Task Name | Status | Start Date | Due Date | Assigned To | Flagged | Description
GET STARTED WITH THIS PROJECT TEMPLATE | Not Started |  |  |  | Flagged | This project template is designed to you to effectively plan a small to medium-sized event with a 6 week lead time, covering all the areas required to make sure it's a success.
INITIAL PLANNING - 6+ WEEKS PRIOR TO EVENT | Not Started |  |  |  | Flagged | When planning a smaller event, you still need to leave plenty of time to give notice to your audience and other stakeholders.
Create Event Overview | Not Started | 2020-06-22 | 2020-06-22 |  | Not Flagged | The event overview helps to set the frame for your event and to lay out all of the key points for it. > Define the purpose of the event > Choose the format (e.g. awards night, conference, presentation, etc.) > Select a date for the event > Set a budget > Create the event's title > Create a shortlist of locations to host the event > Plan the times for the event.
Define Event Scope | Not Started |  | 2020-06-24 |  | Not Flagged | > State the target audience > Plan the messaging > Outline the objectives of the event > Prepare the guest list (e.g. speakers, exhibitions, etc.) > Prepare a risk management checklist > Finalize the budget.
Booking the Venue | Not Started | 2020-06-27 | 2020-06-28 |  | Not Flagged | You'll need to make sure you find the right venue to cater for your event for the date that you've got planned. > Research venue options (availability, layout, capacity, cost, parking, etc.) > Confirm venue booking - pay deposit / sign contracts > Develop risk assessment plan (e.g. emergency exits, contacts, first aid, security) > Clarify if the venue is providing insurance or if you need to book (book accordingly).
Establish Event Publicity Plan | Not Started |  | 2020-06-27 |  | Not Flagged | What needs to be done, who will do it, and when? > Design any assets that can help to support promotion of event > Prepare printed promotional materials (if applicable).
Planning Core Participants | Not Started |  | 2020-06-28 |  | Not Flagged | > Decide if there will be catering (if yes, research & book) > Decide if there will be entertainment required (if yes, research & book) > Prepare a list of possible key guests / speakers to contact.
4-5 WEEKS BEFORE EVENT | Not Started |  |  |  | Flagged
Book Guests / Speakers | Not Started |  | 2020-06-30 |  | Not Flagged | > Contact guests / speakers from the short list > Decide if MC is required - book from short list > Clearly & precisely articulate your goals for the event > Clarify their availability and total cost (travel, accommodation, transfers, etc.) > Obtain food & beverage rider especially any special dietary requirements > Research any technology they'll need - audio-visual equipment etc. > Confirm booking (paying any deposit etc. required).
Prepare Assets for Event |  | 2020-07-02 | 2020-07-07 |  | Not Flagged | > Organize room decoration (if applicable) > Identify how guests will access venue (e.g. public transport, parking, etc.) > Confirm green room facilities. Are they sufficient for guests / speakers? > Obtain menu (if food is being served) for guests, speakers & patrons > Brief the speakers on the event and what to expect.
Begin Promoting the Event | Not Started | 2020-07-07 | 2020-07-28 |  | Not Flagged | Depending on the target audience and the distance that they will have to travel, you'll need to choose the best way to get in contact with them. > Update your website, social media & ask partners to do the same > Identify channels for contacting and inviting guests (Meetup, LinkedIn, Facebook, Twitter, Email, Phone, etc.) > Send invites to target guests > Create & send a press release.
2-3 WEEKS BEFORE EVENT | Not Started |  |  |  | Flagged
Confirm Attendance & Other Requirements | Not Started |  | 2020-07-16 |  | Not Flagged | > Collect RSVPs to confirm final numbers > Print name tags (if required) > Update the run sheet and share with all parties, including floor plan & contact names / numbers for the day > Confirm transfer / parking arrangements for the event > Confirm staff / volunteer numbers to host event > Prepare run sheet and distribute to all parties.
Confirm Venue & Logistics | Not Started |  | 2020-07-16 |  | Not Flagged | Confirm that everything is still on track with the venue
DAY BEFORE EVENT | Not Started |  |  |  | Flagged
Finalize Preparation for Event | Not Started | 2020-07-24 | 2020-07-28 |  | Not Flagged | > Finalize parking arrangements for speakers, entertainment, patrons, volunteers etc. > Notify everyone accordingly.
Update Run Sheet (if required) | Not Started | 2020-07-27 | 2020-07-28 |  | Not Flagged
Undertake Soundcheck & Visuals | Not Started | 2020-07-28 | 2020-07-28 |  | Not Flagged
DAY OF EVENT | Not Started |  |  |  | Flagged
Update Run Sheet (if required) | Not Started |  | 2020-07-29 |  | Not Flagged | Communicate any last minute changes to the run sheet
Conduct Event Set Up |  |  | 2020-07-29 |  | Not Flagged | > Room set up (tables, chairs, lectern, AV, lighting, etc.) > Prepare registration desk (if required) > Display name tags > Set up signs > Run through the event with key stakeholders (MC, speakers, entertainment, etc.) > Have VIP gifts to hand (if relevant) > Ensure audio visual set up is running per schedule > Room dismantle.
POST-EVENT WEEK 1 | Not Started |  |  |  | Flagged | When the event is over and everyone is gone home, there's still some post-event work which needs to be completed. These allow you to round up the event and to gather valuable feedback to help you determine the level of success.
Prepare Post Event Follow Up | Not Started |  | 2020-08-05 |  | Not Flagged | > Collect guest / speaker / volunteer feedback > Prepare thank yous for all parties involved (e.g. speakers, patrons, entertainment, committee etc.) > Review event's performance vs. expectations > Pay any outstanding fees to suppliers, speakers, staff, etc.
All text and design is copyright © Project Central 2020 ¦ All rights reserved ¦ Made with 💙 in Ireland
Formulas:
Due Date = [Start Date]
Due Date = [Start Date, row above]+2

## Disclaimer
Any articles, templates, or information provided by Project Central on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.